## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 21
PROJECT NAME | Question Bank Service for Virtual Labs
PROJECT MENTOR (sponsor) | Virtual Labs
TEAM MEMBERS | Ansh Chablani
Divyarajsinh Mahida
Shreyas Badami
Siddharth Singh

## Status
PROJECT NUMBER | 21 |  |  |  | Done
PROJECT NAME | Question Bank Service for Virtual Labs |  |  |  | Planned
PROJECT MENTOR (sponsor) | Virtual Labs |  |  |  | Ongoing
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 21 - January 28)
Fix meeting with client | Coordination | Project Mentor | 1 | 1 | Done | Introductory Meeting | 0 | 0
GitHub and GitLab Repository setup | Preparation | All | 0.6 | 1 | Done |  | -0.4 | 40
Understand JSON Schema | Preparation | All | 1 | 1.5 | Done |  | -0.5 | 33.3333
Make Status Tracker | Documentation | Ansh, Divyaraj | 1.5 | 2 | Done |  | -0.5 | 25
Write Minutes of Meeting | Documentation | Ansh, Divyaraj | 0.5 | 0.6 | Done |  | -0.1 | 16.6667
Project Synopsis | Documentation | Ansh, Divyaraj | 1 | 1.5 | Done |  | -0.5 | 33.3333
Identify role owners | Coordination | All | 0.3 | 0.3 | Done | Deciding on backend vs frontend separation | 0 | 0
Decide on Technologies - Backend | Preparation | All | 1 | 1 | Done |  | 0 | 0
Decide on Technologies - Frontend | Preparation | All | 1 | 1 | Done |  | 0 | 0
Week 2 (January 28 - February 4)
Design of Authentication Screen | Design | Ansh, Divyaraj | 3 | 2 | Done | Made functional
Build frontend for authentication | Development | Siddharth, Shreyas | 4 | 5 | Done | Done | -1 | 20
Build backend for authentication | Development | Ansh, Divyaraj | 5 | 6 | Done | Done | -1 | 16.6667
Designing of main screens | Design | All | 5 |  | Planned | Priority order changed, so this is postponed to a future sprint.
Week 3 (February 4 - February 11)
Responsive Navbar UI component | Development | Siddharth | 5 | 6 | Done | Built to a functional extent, may modify later | -1 | 16.6667
Basic Question Input form | Development | Siddharth, Ansh | 8 | 5 | Done | Built to a functional extent, will modify later | 3 | 60
Tag Selection with Auto Complete Frontend | Development | Siddharth | 6 | 5 | Done | Built to a functional extent, to modify later | 1 | 20
Dashboard Design | Design | All | 4 | 0 | Planned | Priority order changed, so this is postponed to a future sprint. | 4
Week 4 (February 11 - February 18)
Design a question input system. | Design | Ansh | 5 | 7 | Done | Done | -2 | 28.5714
Add functionality to add Latex/Markdown input. | Development | Siddharth | 5 | 5 | Done | Latex rendering remains but that would be put as a separate topic since most of the framework is done. | 0 | 0
Implement functionality of buttons and input. | Development | Ansh | 7 | 5 | Done | Done to an extent that was in the scope of the current iteration, would do multiple times across the project timeline. | 2 | 40
Send final question to backend server. | Development | Shreyas | 4 | 3 | Done |  | 1 | 33.3333
Add functionality to upload an image. | Development | Divyaraj | 4 | 3 | Done | Done what was planned, but some specs changed and we would have to make slight modifications, which we shall mention as a new topic | 1 | 33.3333
Week 5 (February 18 - February 25)
Design a question display system | Development | Ansh, Siddharth | 5 | 4 | Done | Fast prototype, less focus on aesthetics, refinements in next iterations. | 1 | 25
Integrate Basic Question Display Screen | Development | Siddharth | 4 | 4 | Done | Same as above | 0 | 0
Do extensive review | Coordination | All Team Members | 2 | 0 | Delayed | Review for early prototype deployement | 2
Do system testing | Testing | All Team Members | 3 | 0 | Delayed | Review for early prototype deployement | 3
Week 6 (February 25 - 3 March )
Fix equation display in preview, add latex | Development | Siddharth | 1 | 4 | Done | Need to add LaTeX for equations. | -3 | 75
Integrate Auth UI and Backend | Development | Ansh | 4 | 5 | Done | Integration work for end-month sample deployement requested by client | -1 | 20
Integrate Question Bank Input and Auth | Development | Divyaraj | 4 | 4 | Done | Same as above | 0 | 0
Download selected Questions Feature | Development | Siddharth | 5 | 5 | Done |  | 0 | 0
Integration testing for Auth UI and Backend | Testing | Divyaraj | 1.5 | 3 | Done | Same as above | -1.5 | 50
Week 7 (March 3 - 10 March )
Deploy service to Backend | Delivery | All | 5 | 3 | Done | Sucessfully done! | 2 | 66.6667
Integration testing for Question Bank Input and Auth | Testing | Ansh, Siddharth, Divyaraj | 1.5 | 2 | Done | Integration Testing for the Implement Application - Done manually | -0.5 | 25
Integration testing for Question Display Screen | Testing | Ansh | 1.5 | 2 | Done | Same as above | -0.5 | 25
Add security features and access restriction | Development | Siddharth | 3 | 3 | Done | Now an access restricted sceen is shown on using the app without logging in. | 0 | 0
UX Enchancement | Design | Ansh | 8 | 3 | Done | Need to enchance the looks of the system to some extent | 5 | 166.6667
Week 8 (March 10 - 17 March )
Prepare Preliminary Documentation | Documentation | All | 5 | 4 | Done | Prepare preliminary documentation | 1 | 25
Adding UX enhancement for more screens | Design | Ansh | 6 | 6 | Done | Enchance the looks of the system | 0 | 0
Automated testing for the application. | Testing | Ansh, Divyraraj | 8 | 10 | Done | Do automated testing (preferably selenium) | -2 | 20
Complete Design Documents | Documentation | All | 10 | 8 | Done | Documentation as required | 2 | 25
Week 9 (March 17 - 24 March )
Test respository hosting | Testing | Ansh | 4 | 5 | Done | Testing the above | -1 | 20
Add Admin Screen | Interfaces | Siddharth | 4 | 4 | Done | As part of new use case | 0 | 0
Improve Looks | Design | Ansh | 3 | 2 | Done | UX Enhancement | 1 | 50
Change Password Option | Development | Divyaraj | 4 | 5 | Done | To Update Details | -1 | 20
Make User Profile Screen | Interfaces | Divyaraj | 2 | 2 | Done | As a planned screen | 0 | 0
Test CRUD Operations | Testing | Siddharth | 3 | 4 | Ongoing | Testing Admin Screen's CRUD Operation | -1 | 25
Week 9 (March 24 - 31 March)
Separate Out Backend wioth Frontend | Development | Divyaraj | 12 | 8 | Done | Client requirements changed / were unclear, they want different hostings now | 4 | 50
Design Backend APIs | Design | Divyaraj | 3 | 3 | Done | APIs for a middleware applications | 0 | 0
Add Markdown Support | Development | Siddharth | 4 | 4 | Done | For Questions, Answers and Explanations | 0 | 0
Week 9 (March 31 - 7 April)
Add Autocorrect Feature | Development | Divyaraj | 5 | 6 | Done | As part of new use case | -1 | 16.6667
Add Google Authentication | Development | Ansh | 4 | 3 | Done | As per Client's request | 1 | 33.3333
Achieve major responsiveness | Development | Siddharth | 5 | 4 | Done | Making it mobile friendly | 1 | 25
Image Upload | Development | Ansh | 5 | 5 | Done | Add feature to upload image | 0 | 0
Week 10 (March 7 - 15 April)
Improve API Cases | Development | Divyaraj | 10 | 9 | Done | For a smoother backend | 1 | 11.1111
Fix per page view | Development | Siddharth | 5 | 4 | Done | Fixing a bug | 1 | 25
Add Image View on Questions | Development | Ansh | 5 | 4 | Done | Adding functionality of Image View | 1 | 25
Add multi-tag search | Development | Siddharth | 5 | 4 | Done | Adding functionality of search through many tags. | 1 | 25
Week 9 (March 15 - 20 April)
Write Automated Tests | Testing | Ansh | 10 | 10 | Done | For testing | 0 | 0
Handle edge cases | Testing | Divyaraj | 5 | 5 | Done | Completeness | 0 | 0
Complete Documentation | Documentation | Divyaraj | 10 | 10 | Done | Documentation as required | 0 | 0
Deploy on the web | Delivery | Ansh | 4 | 4 | Done | Deployement part | 0 | 0
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically